## Sheet1
Project Name | Mifos Mpesa Integration
Project Manager | Dalmas Chituyi
Start Date | 2023-05-04
End Date | 2023-06-07
Overall Progress | 35%
Tasks | Responsible | Start | End | Days | Status | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07
2023-05-05
Set kick-off meeting | Dalmas Chituyi | 2023-05-05 | 2023-05-05 | 1 | Complete
Agree on objectives | Dalmas Chituyi | 2023-05-05 | 2023-05-05 |  | Complete
Initiation
Detailed Reqs. | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Hardward Reqs. | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Final Resource Plan | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Staffing | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Development |  |  |  |  | Ongoing
Techincal Reqs. | Dalmas Chituyi | 2023-05-13 | 2023-05-13 |  | Complete
DB Development | Dalmas Chituyi | 2023-05-13 | 2023-05-14 |  | Complete
API Development | Dalmas Chituyi | 2023-05-07 | 2023-05-25 |  | Halfway done!
Get Existing API | Dalmas Chituyi | 2023-05-10 | 2023-05-12
Buy SSL Certificates- Mifos, Tadeo | Levi | 2023-05-11 | 2023-05-12
Start registration of another API |  | 2023-05-10 | 2023-05-24 | milstone
Update Mifos DB with Staging DB |  | 2023-05-12 | 2023-05-24 | milestone
Testing | Dalmas Chituyi | 2023-05-25 | 2023-05-27 |  | Not started
Documentation |  | 2023-05-12 | 2023-05-29
Go Live |  | 2023-05-28 | 2023-05-30 | milestone
Support After Implementation |  | 2023-05-30 | 2023-11-30
Milestone
Launch |  |  | 2023-05-07

## Sheet2
Project Name | FAWE WEB APP
Project Manager | Harrison Muthee
Start Date | 2023-05-25
End Date | 2023-07-05
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07
2023-05-05
Set kick-off meeting | Harrison Muthee | 2023-05-05 | 2023-05-05 | 1 | Complete
Agree on objectives | Harrison Muthee | 2023-05-05 | 2023-05-05 |  | Complete
Initiation
Detailed Reqs. | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Hardward Reqs. | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Final Resource Plan | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Staffing | Dalmas Chituyi | 2023-05-06 | 2023-05-06 |  | Complete
Development |  |  |  |  | Ongoing
Techincal Reqs. | Dalmas Chituyi | 2023-05-13 | 2023-05-13 |  | Complete
Frontend Development | Harrison Muthee |  |  |  | Halfway done!
Sign In And Login form | Harrison Muthee
User Pages | Harrison Muthee
Pages | Harrison Muthee
Admin Dashboard | Harrison Muthee
DB Development | Dalmas Chituyi | 2023-05-13 | 2023-05-14 |  | Complete
API Development | Dalmas Chituyi | 2023-05-07 | 2023-05-25 |  | Halfway done!
Get Existing API | Dalmas Chituyi | 2023-05-10 | 2023-05-12
Buy SSL Certificates- Mifos, Tadeo | Dalmas Chituyi | 2023-05-11 | 2023-05-12
Testing | Dalmas Chituyi | 2023-05-25 | 2023-05-27
Documentation |  | 2023-05-12 | 2023-05-29
Go Live |  | 2023-05-28 | 2023-05-30 | milestone | Not started
Support After Implementation |  | 2023-05-30 | 2023-11-30
Milestone
Launch |  |  | 2023-05-07